## Slide 1
STAYORA · CAPSTONE EXECUTION PLAN
Three Days to a
Working Concierge
Thu Aug 20 → gap → Sun Aug 23 → Mon Aug 24
Not consecutive — Day 1 has to land in a state you can walk away from for two days and pick back up cold.
STAYORA — CAPSTONE EXECUTION PLAN
01 / 08

## Slide 2
WORKING ASSUMPTIONS
Scope, before anything else
ROUTESTACK
Live API access confirmed
wire direct — no mock layer
LLM
Claude API (Sonnet)
recommended for reliable tool-calling
DATABASE
Postgres
hosted free tier — Neon or Supabase
SCAFFOLDING
Reuse Week3Day4 / Week3Day5
MCP server + RAG/orchestrator patterns
Three days is demo/capstone scope, not production: no full auth system, no payment processing. Reservations go through RouteStack's sandbox/test mode.
STAYORA — CAPSTONE EXECUTION PLAN
02 / 08

## Slide 3
DAY 1 THU · AUG 20
The backbone
GOAL A real natural-language query returns real ranked hotels — pulled live through an MCP tool layer wrapping RouteStack. No RAG, no booking yet: just Understand → Search, working end to end.
45m
Scaffold the repo: Node.js + Express, type: module, folders mirroring Week3Day5 — src/mcp, src/rag, src/agents, src/orchestrator. .env, README stub.
2h
MCP tool server (src/mcp/routestackServer.js) via @modelcontextprotocol/sdk + zod: search_hotels, get_rates, get_policy as typed wrappers over RouteStack, normalized JSON out.
1.5h
Understand step: Claude call turning free text ("boutique hotel near downtown Austin, under $250/night, flexible cancellation, next weekend") into structured intent JSON. Test against 5 sample prompts.
2h
Orchestrator v1: Understand → search_hotels → ranked-list response, sorted by price/rating for now. Expose as POST /chat.
1h
Smoke test with 3 real scenarios against live RouteStack; log every request/response pair to a file — the seed of the audit trail.
30m
Commit. Write PROGRESS.md: exact state, open questions, next three steps. This is what Sunday-you reads first.
SHIPS TODAY POST /chat returns real, live RouteStack results from a plain-English request.
STAYORA — CAPSTONE EXECUTION PLAN
03 / 08

## Slide 4
DAY 2 SUN · AUG 23
Recommend, reserve, and a face
GOAL The full agentic loop — Understand → Search → Recommend → Reserve — grounded in RAG for policy reasoning, with a real price re-check and confirmation gate before anything books. Plus a chat UI a person can actually use.
30m
Re-orient: read PROGRESS.md, re-run the Day 1 smoke test to confirm RouteStack and env still behave.
2h
RAG layer: seed src/rag/knowledge/ with cancellation-policy explainers, a "how Stayora ranks" guide, sample preference profiles. Reuse Week3Day5's buildIndex.js embedding pipeline.
2h
Recommend agent: rank Day 1's results using preferences + RAG-retrieved policy context, generate the explanation ("free cancellation until 48h, 4.6★, matches downtown") — the deck's core differentiator.
2h
Reserve agent with safety checks: re-fetch price via get_rates right before booking to catch drift, require explicit confirmation, then call create_booking against RouteStack. Log every attempt.
1.5h
Postgres: minimal schema — sessions, reservations, saved_preferences. Wire confirmed bookings to persist.
1.5h
Frontend v1: React + Tailwind chat view — message thread, hotel comparison cards, inline confirm-before-book. Wired to /chat and /confirm-booking. No auth UI.
30m
Commit, update PROGRESS.md.
SHIPS TODAY Chat "find me a hotel…" in the browser, get an explained recommendation, confirm it, and a real reservation lands in RouteStack and Postgres.
STAYORA — CAPSTONE EXECUTION PLAN
04 / 08

## Slide 5
DAY 3 MON · AUG 24
Ready to show
GOAL Demoable without babysitting, and visibly matching what the deck promises: an orchestrator, distinct agents, a RAG layer, and an MCP tool boundary — not one script pretending to be four things.
1.5h
Guardrails (reuse the Week3Day5 pattern): graceful handling of RouteStack errors, no-results, ambiguous intent; refuse to book without explicit confirmation; a best-effort fallback if an agent step fails.
1h
Evaluation script (reuse evaluate.js): 8–10 scripted scenarios — happy path, price drift, no availability, ambiguous request, policy question — run automatically, pass/fail logged.
2h
UI polish pass: loading/typing states, comparison-card hierarchy, confirmation modal, empty/error states, a mobile-reasonable layout.
1h
Architecture sanity check against slide 7: confirm the four boxes — Orchestrator, Agents, RAG, MCP→RouteStack — are actually distinct in the running code and logs.
1h
README + a 3-scenario demo script: a clean booking, a caught price-drift, a policy question. Plus setup instructions.
1h
Record a 2–3 min demo clip as a fallback in case the RouteStack sandbox is flaky live.
30m
Buffer — bug bash on whatever broke.
SHIPS TODAY A rehearsed, demoable Stayora that matches every claim on the Solution and Architecture slides.
STAYORA — CAPSTONE EXECUTION PLAN
05 / 08

## Slide 6
BEFORE DAY 1 — WEDNESDAY NIGHT, ~30 MIN
Prep, not build
✓
RouteStack docs
Confirm base URL, auth method, rate limits, sandbox/test mode. Get keys into .env tonight, not Thursday morning.
✓
Credentials ready
Anthropic API key ready, and a Postgres connection string from a free Neon or Supabase project.
✓
Endpoint field names
Skim RouteStack's search / rates / policy / booking endpoints — their field names decide the MCP tool schemas you write first thing Thursday.
STAYORA — CAPSTONE EXECUTION PLAN
06 / 08

## Slide 7
NAMED EARLY, NOT DISCOVERED LATE
Risks worth naming now
!
RouteStack sandbox availability or rate limits
Verify Wednesday night, not mid-build Thursday.
!
Business-model scope creep
The B2B/white-label and premium-subscription slides are pitch narrative, not a Day 3 feature request.
!
Hosted Postgres latency from a Windows dev box
Test the connection Day 1, before Day 2 depends on it for every booking.
STAYORA — CAPSTONE EXECUTION PLAN
07 / 08

## Slide 8
STAYORA · CAPSTONE EXECUTION PLAN
Three days. One working
agentic concierge.
Drafted for the build spanning Aug 20–24, 2026.
08 / 08